## Sheet1
PROJECT OVERVIEW
Project: 100,000 Colored Wall Calendars for MCWD
Unit Cost: ₱42.34
Total Contract Value: ₱4,234,456.58
Date Binding Proper : August 4, 2025
Award Timing: Binding Proper
Delivery Schedule:
30% (30,000 pcs) within 30 calendar days from award
70% (70,000 pcs) on or before November 28, 2025
LIMITING FACTOR: MACHINE UPGRADE — SM-102 HEIDELBERG (6-COLOR)
Required Actions for Preventive Maintenance & Calibration
Component | Action Required | Hours | Priority
1.Gripper Units | Calibration of all gripper units | 6–8 | High
2.Delivery Gripper | Calibration and alignment | 4 | High
3.Dampener | Cleaning, alignment, pressure calibration 6 | 6 | Medium
4.Plate Clamp | Check locking mechanism, realign | 3–4 | High
5.Chiller System | Installation and testing | 12–16 | Critical
6.Inker System | Calibration of rollers and inking units | 8 | High
7.Dampening Holder | Inspection and replacement (if worn) | 3 | Medium
Total Estimated Downtime for Maintenance/Upgrade: 42–49 hours (approx. 5–6 working days)
ACTION PLAN & TIMELINE
PHASE 1: Maintenance & Pre-Production (Week 1–2)
Task | Responsible | Timeline (Days) | Notes
Approve and schedule machine calibration | Operation Manager | Day 1–2 | Internal alignment
Perform machine maintenance & upgrade | Technical Team | Day 3–7 | Ensure 100% readiness
Finalize design & proofing with MCWD | Graphics/QC | Day 3–5 | Color approval
CTP (Plate-making) | Prepress | Day 6–7 | For first batch
Procure materials (paper, ink, binding supplies) | Purchasing | Day 1–7 | Allow overlapping
PHASE 2: Production for 30% (30,000 pcs) (Week 3–4)
Task | Target Output | Timeline | Notes
Printing (1st batch) | 6,000 pcs/day avg | Day 8–14 | Allow 2-shift run
Cutting & Binding | Daily parallel | Day 9–16 | Loop with printing
QC, Packing, and Staging | 5,000–6,000/day | Day 12–18 | Sequential loading
Delivery of 30% (30,000 pcs) | - | Day 25–30 | Confirm receipt
PHASE 3: Production for 70% (70,000 pcs) (Week 5–10)
Task | Target Output | Timeline | Notes
Printing (2nd batch) | 7,000 pcs/day avg | Day 20–42 | Enhanced pace
Binding, QC, and Packing | 7,000/day | Day 21–44 | Ensure consistency
Final Delivery Prep | 70,000 pcs | Day 45–50 | Schedule staging
Final Delivery Deadline | Nov 28, 2025 | Before Day 50 | Avoid penalties
RESOURCE ALLOCATION
Department | Roles
Technical Team | Machine calibration/repairs
Prepress/Design | Final artwork & plates
Production | Printing, binding
QC | Color matching, registration
Logistics | Packing, delivery coordination
Admin | Timeline, budget tracking
QUALITY & RISK MITIGATION
Risk | Mitigation Strategy
Machine downtime | Preventive maintenance before production
Chiller installation delay | Secure unit by Week 1
Paper supply delay | Pre-book order and verify delivery lead time
Output rejection (QC issue) | Mid-run and post-run inspection
Binding bottleneck | Assign multiple finishing operators
DELIVERY PLAN
Batch 1: 30% (30,000 pcs)
Due Date: 30 calendar days after award
Delivery Method: Staggered in 2–3 truckloads
Packing: Labeled by batch and quantity
Batch 2: 70% (70,000 pcs)
Due Date: On or before November 28, 2025
Delivery Method: Split across multiple trips or bulk drop
Packing: Uniform packaging, QC sealed
FINAL REMARKS
Allocate Week 1–2 for full equipment prep and final approvals.
Begin rolling production and delivery starting Week 3.
Utilize 2-shift operations to meet output goals efficiently.
Monitor via a daily progress log and delivery tracker.